Cabarrus Partnership for Children

2025-2026

NCPK Implementation Processes

- Outreach- Beginning in January- Tuesdays and/or Thursdays Lissy and TeeTee alternate going into the community to outreach as businesses, parks and apartments.

- Outreach and advertising

    - Community Visits (Businesses, parks, neighborhoods, etc.)

    - Social Media Blast (Starting in Dec to start taking apps in Jan)

    - Public Schools send out information (connect Ed, flyers, etc.)

    - Recruit at Community Events

- Partnership and Committee Responsibilities (July-June)

- Appoint site-selection committee to approve sites for the new contract cycle.

- Approve Local Plan

  - Contracting agency

  - Written Suspension & Expulsion Plan

  - Written Family Engagement Plan

  - Written ESL Plan

  - Written Transportation Plan

  - Written Transitions Plan

  - Review Inclement Weather Policy

  - Review Plan for health consultation

- Review State Contract

- Review Budget

- Sign Section 1 Assurances

- Slot allocations – Late May-Early June depending on State Contract

- Enter committee and contact info into NCPK Plan

- Site Selection-(Dec-March)

- Site Information meeting November 5, 2025, for the 2026-2028 contract cycle.

- Site Selection Committee convene on Feb. 5 (Training)

    - Site selection process February 4, 2026- March 11 2026

    - Site recommendations to Committee on March 18th at regular committee meeting

    - Sites will be notified the first week of April.

- Child Applications taken between January 1- November 15th

- Applications turned into office via, JotForm, email, drop boxes, fax and in-person.

  - Applications processed and added to active waitlist when complete after 1st and 2nd audit)

  - Parent given screening appointment (1st round to be done late May)

- Files processed and data entered in NCPK App (when file is complete)

- 1st file assembled and audited to determine eligibility

- 2nd file audit (Determine TNAF and NON-TANF, closest location)

- Data entered NCPK App (Eligibility) –generate scorecard

- Sort for 1st round placements from spreadsheet (according to eligibility (TANF/Non-TANF) and closest)

- Head Start Dual Funding File 2nd Audit

  - Head Start files due to CPFC by July 17, 2025

- Screening Planning (April-May)

- Coordinate with CCS and KCS (if possible)

- Start planning for placement at screening

- Child files sorted by site according to eligibility and first round allocations

- Determine how many contract staff are needed for screening and placement.

- Screening and Placement

- Schedule screening appointments at 10 every 45 minutes (?)

- Family Questionnaires

- Sign up for Dolly Imagination Library

- Placement offered after screening complete if no significant concerns

  - Files organized by site and eligibility status

  - Placement option offered to families according to priority list for each site.  Lowest income families are given priority.

  - Waitlist letter for families not offered 1st round

  - Double-check the number of confirmed placements for all sites.

- Week after placement week,

  - Resort files and waitlist

  - offer placement via phone for any spots not filled from priority list for each site (only if file is complete with Dial and screenings)

  - Copy Dial forms for office file

  - Copy files for sites-Original Dial placed in site file

- Planning for 2nd screening event (early July)

  - Follow process for initial apps and scheduling

  - Second Round of Screening in Mid-July or early August?

    - Coordinate with CCS and RCCC, KCS and CHS (Dental)

- Second Round Slot Allocation-July Meeting (based on current waitlist)

  - Placement for remaining slot allocations from waitlist

- NCPK Plan App (May-August)

- Update Committee Information

- Enter child information into NCPK Kids (Placement)

- Site Information

  - Administrators (From collected documentation)

  - Teachers (From collected documentation)

  - Children (NCPK Kids)

  - Site year end dates

  - Classroom info (#children, payment rates)

- Section II Signatures (All site Administrators)

- Child Files- Sent to NC Pre-K Site each child is assigned to.

- Child files for each site are copied.

- Original Dial Record Sheet is included with the file (copy is put in office file)

- Second signature file audit for McKnight dual funded slots in June

- Site Administrator’s New Year Orientation-

  - June 24, 2025

- NCPK Site Staff Training and Orientation (August)

- NCPK Guidelines and Requirements

- Local Guidelines and Requirements

  - Suspension and Expulsion

  - Family Engagement

  - Working with ESL Families

  - Transitions

- Curriculum and Assessment

  - CC and TSG

- Attendance Requirements and Procedures

- Attendance and FSRs

- Attendance forms due from sites by 11:00am last attendance day of the month.

- Attendance for each site entered NCPK Kids App

  - Reports printed, signed by Program Manager

  - Site Admins to DocuSign reports by deadlines given

    - 2nd signature forms must be on file

    - Reimbursement packets sent to DCDEE for payment

- Attendance forms filed at CPFC office

- FSR’s Due to DCDEE by 10th of each month

- Termination forms turned in by sites ASAP

- New children added to attendance sheet by site staff

- Staff Development

- Curriculum and Social-Emotional offered through-the school year

- Teaching Strategies Gold offered by DCDEE online

- LETRS Training as required by North Carolina law.

- Site Monitoring

  - Site monitoring Tools due by Oct. 15

  - Scheduled site monitoring visits Nov-Jan

  - Monitoring Review Completed by onsite, virtual or desk review by Jan. 15th

  - Unannounced site visits are made throughout the school year as needed.

  - Kindergarten Transition parent meetings in April

  - Ongoing classroom support and teacher coaching Aug- June